Verner Grid Systems Inc.

NB Power Engineering Platform

Protection & Control Information Management, Settings, Compliance, and Analytics Platform

Proposal to New Brunswick Power | Phase 1 Platform Foundation and Future Roadmap

| Field | Detail |
| --- | --- |
| Prepared for | New Brunswick Power |
| Submitted by | Verner Grid Systems Inc. |
| Principal contact | Daren Verner, P.Eng., President & Principal Consultant |
| Date | June 29, 2026 |
| Commercial basis | $48,000 CAD fixed price; HST excluded |
| Primary phase | Phase 1 - Platform Foundation / Relay Settings Book and Workflows |

# 1. Executive Summary

The NB Power Engineering Platform is a staged engineering-software program that begins with replacement of the existing relay settings and device-management application and expands into asset management, configuration management, compliance support, event analysis, and engineering analytics.

Phase 1 delivers the platform foundation: a Relay Settings Book and workflow-driven application backed by Microsoft SQL Server and accessed through a browser-based interface. It includes role-based access control, controlled document management, legacy migration support, reporting parity for acceptance, and architecture suitable for later integration.

This proposal offers the proposed Phase 1 implementation scope on a fixed-price basis. Phase 1 acceptance is tied to the authorized scope, acceptance criteria, assumptions, and exclusions below.

# 2. Scope of Work

## 2.1 Phase 1 Objective

Establish the core P&C information-management platform and Relay Settings Book as a secure web-based system that manages relay setting documentation, engineering workflow state, approvals, revision history, and supporting metadata.

## 2.2 Included Phase 1 Capabilities

Browser-based application interface for engineering and technical users.

Microsoft SQL Server central repository for P&C records, metadata, and document relationships.

Active Directory authentication with role-based access control.

Relay Settings Book records for active, historical, and archived settings documentation.

Cradle-to-grave document history including creation, revision, review, approval, issuance, replacement, retirement, and archive status.

Controlled document storage and publishing workflow for Word/PDF settings documentation and associated files.

Workflow states and status tracking sufficient to emulate the current completion-tracking process and support later expansion.

Legacy data migration planning and basic migration of current flat database content and rationale documents.

Reporting and views equivalent to the legacy application for Phase 1 acceptance.

Integration readiness and interface design for Cascade, SAP, ASPEN OneLiner, Line Constants, and other approved systems.

## 2.3 Future Roadmap

| Phase | Outcome | Status |
| --- | --- | --- |
| Phase 1 | Platform foundation, Relay Settings Book, workflows, document control, migration, and integration readiness. | Near-term |
| Phase 2 | Asset management, installed-base records, lifecycle status, and replacement planning. | Planning |
| Phase 3 | System modelling, transmission line modelling, mapping, ASPEN export, and validation. | Planning |
| Phase 4 | Event warehouse, event viewing, timeline reconstruction, and fault-location support. | Planning |
| Phase 5 | Engineering analytics, deterministic model validation, and issue reporting. | Planning |

# 3. Technical Approach

The platform will follow the current PNC Platform architecture rather than the obsolete C++Builder application structure. The backend will expose thin API handlers over repository/domain modules, and the frontend will provide an operational React/Vite browser interface. Device settings storage, validation, parsing, adapters, and normalized application fields will follow the project device-configuration model.

| Area | Approach |
| --- | --- |
| Database | Microsoft SQL Server as the central authoritative repository with referential integrity, auditability, and future integration readiness. |
| Application | Browser-based user interface for relay settings records, equipment metadata, workflow status, document history, and reports. |
| Security | NB Power Active Directory authentication with configurable role-based permissions for read, modify, approve, archive, and report functions. |
| Data model | Cascade functional locations used where applicable, with P&C-specific cross-reference and hierarchy for engineering granularity. |
| Documentation | Database documentation package, deployment/runbook material, training references, and acceptance evidence appropriate to the authorized phase. |

# 4. Phase 1 Scope Composition

The SOW contains a Phase 1a implementation baseline and additional Phase 1 deliverables. The $48,000 CAD fixed price is based on the complete Phase 1 implementation basis used for this proposal: the Phase 1a baseline plus the added Phase 1 deliverables and hourly expectations shown below. This distinction is made to show how the price was built, not to remove the added Phase 1 work from the fixed-price offer.

| SOW Deliverable | Phase 1a Baseline | SOW Hours | Fixed-Price Phase 1 Treatment |
| --- | --- | --- | --- |
| Core application + database | Included | 45-55 | Included in the proposed fixed-price Phase 1 scope. |
| Legacy data migration (basic) | Included | 10-15 | Included for representative/basic migration needed to commence cutover. |
| Reporting parity | Included | 10-15 | Included for legacy replacement acceptance. |
| Requirements specification | Not in Phase 1a | 10-15 | Included as an added Phase 1 deliverable within the fixed price. |
| Functional design document | Not in Phase 1a | 12-18 | Included as an added Phase 1 deliverable within the fixed price. |
| Technical architecture | Not in Phase 1a | 8-12 | Included as an added Phase 1 deliverable within the fixed price. |
| Integration design | Not in Phase 1a | 10-16 | Included for design/readiness; live production integrations remain change-controlled. |
| Document control framework | Not in Phase 1a | 8-12 | Included as an added Phase 1 deliverable within the fixed price. |
| Workflow expansion | Partial | 6-10 | Included to the extent required for the approved Phase 1 implementation. |
| Geographic mapping | Not in Phase 1a | 12-20 | Included only to the extent required by the approved Phase 1 implementation scope. |
| Testing documentation | Not in Phase 1a | 10-16 | Included as an added Phase 1 deliverable within the fixed price. |
| Training materials | Not in Phase 1a | 6-10 | Included as an added Phase 1 deliverable within the fixed price. |
| Operations documentation | Not in Phase 1a | 6-10 | Included as an added Phase 1 deliverable within the fixed price. |
| Database documentation package | Not in Phase 1a | 16-24 | Included as an added Phase 1 deliverable within the fixed price. |

## 4.1 Added Phase 1 Documentation Packages

The SOW identifies several documentation packages that are outside the Phase 1a baseline but included in the full Phase 1 fixed-price basis for this proposal.

High-level system architecture and data-flow diagrams.

Logical and physical entity-relationship diagrams.

Data dictionary covering tables, fields, data types, keys, and validation rules.

Catalog of programmable objects such as stored procedures, functions, triggers, and views where applicable.

Security and governance protocols including role structure, permissions, retention, and archival rules.

Operational runbook including deployment, backup/restore, maintenance, and recovery procedures.

## 4.2 Phase 1 Effort and Deliverable Alignment

For pricing purposes, the SOW work is separated into the Phase 1a core baseline and the additional Phase 1 deliverables and hourly expectations needed for the complete Phase 1 implementation. The fixed price is based on the total Phase 1 effort, not the 80-hour Phase 1a baseline alone.

| Item | Value |
| --- | --- |
| Phase 1a core implementation baseline | ~80 hours |
| Additional Phase 1 deliverables and expectations | ~104-163 hours |
| Total Phase 1 fixed-price effort basis | ~180-240 hours |

# 5. Acceptance Criteria

Authorized users can sign in through NB Power Active Directory or approved test equivalent.

Role-based permissions restrict read, modify, approve, archive, and reporting capabilities according to the agreed matrix.

Relay settings records can be created, searched, edited, reviewed, approved, issued, archived, and traced through revision history.

Legacy data needed for Phase 1 acceptance is migrated or mapped according to the approved migration plan.

Reporting/views required for replacement of the legacy application are delivered and validated by NB Power reviewers.

Only documentation and acceptance evidence authorized for the selected commercial scope are delivered with the production-ready package.

# 6. Commercial Summary

The proposed commercial structure is a $48,000 CAD fixed price for the complete Phase 1 implementation basis described in this proposal. The fixed price is built from the Phase 1a core baseline plus the additional Phase 1 deliverables and hourly expectations, with assumptions, exclusions, and acceptance criteria stated in this proposal.

| Item | Value |
| --- | --- |
| Development rate | CAD $150/hour |
| Phase 1a core baseline | ~80 hours for core application/database, basic migration, and reporting parity. |
| Hybrid Phase 1a fixed component | $16,000 CAD, calculated as 80 hours x CAD $150/hour x 1.333 markup/contingency factor. |
| Additional Phase 1 deliverables and expectations | ~104-163 hours for Phase 1 items beyond the 1a baseline. |
| Total Phase 1 effort basis | ~180-240 hours. |
| Fixed price | $48,000 CAD for the complete Phase 1 implementation basis described in this proposal. |
| Pricing basis | Fixed price uses the high end of the total Phase 1 effort band with commercial markup/contingency. |
| Tax | HST excluded. |

| Commercial Option | Description | Scope Control |
| --- | --- | --- |
| A - Hourly | Complete Phase 1 implementation delivered at CAD $150/hour. | Final cost follows actual authorized hours and approved scope. |
| B - Fixed price | Complete Phase 1 implementation basis fixed price of $48,000 CAD. | Applies to the deliverables and acceptance criteria stated in this proposal. |
| C - Hybrid | Phase 1a core baseline fixed/capped at $16,000 CAD, with additional Phase 1 deliverables beyond 1a delivered at CAD $150/hour. | Phase 1a fixed component is calculated as 80 hours x CAD $150/hour x 1.333; added-scope hours are authorized before execution. |

# 7. Schedule

Phase 1 is planned around a four-week delivery target from project start, contingent on infrastructure readiness, access to stakeholders and source data, timely review cycles, and prompt decisions on scope questions. The implementation schedule is established at authorization based on NB Power environment access, test data, and acceptance participant availability.

# 8. Assumptions and Risks

| Risk / Assumption | Mitigation / Planning Note |
| --- | --- |
| Phase 1 scope expansion | Keep acceptance tied to the authorized feature set and handle additional scope through change control. |
| Enterprise integration availability | Live integrations are outside the Phase 1 fixed price unless expressly authorized by written change order. |
| Infrastructure readiness | NB Power provides server, network, workstation, security, and internal deployment infrastructure. |
| Legacy data quality | Use migration mapping and review cycles to identify gaps before production use. |
| NB Power participation | Schedule depends on stakeholder access, timely decisions, data access, and UAT participation. |

# 9. Exclusions

Hardware, server, workstation, network, and NB Power infrastructure procurement.

Live integrations with Cascade, SAP, ASPEN OneLiner, Line Constants, or other enterprise systems, except by written change order.

Full real-time bi-directional enterprise integrations.

Replacement of enterprise asset-management systems.

Full Phase 2-5 capability delivery under the Phase 1 authorization.

Unbounded legacy cleanup, reclassification, or manual data correction beyond the agreed migration scope.

Wholesale migration of all historical engineering records without agreed data-cleansing rules.

Advanced analytics, AI, or automatic settings generation in Phase 1.

Mobile application development.

Changes to NB Power enterprise security, records-retention, or infrastructure policies.

# 11. Authorization

This proposal is submitted by:

| Field | Detail |
| --- | --- |
| Supplier | Verner Grid Systems Inc. |
| Authorized representative | Daren Verner, P.Eng. |
| Title | President & Principal Consultant |
| Authorized signature |  |
| Date |  |